## Sheet1
Task | 2024-02-26 |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | 2024-08-29
|  | WK 01 | WK 02 | WK 03 | WK 04 | WK 05 | WK 06 | WK 07 | WK 08 | WK 09 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27
Supervisor meetings | bar: March WK 02; April WK 06; May WK 11; June WK 15; July WK 19; July WK 22; 2024-08-29 WK 24; 2024-08-29 WK 26
Study deep reinforcement learning & Unity ML-Agents toolkit | bar: March WK 02 to April WK 07
Documentation & 2D Fighting Game Development
Prepare and update GDD and TDD | bar: March WK 02 to March WK 03; April WK 07; May WK 11; June WK 15; July WK 19
2D asset integration and level design/development | bar: March WK 04 to March WK 05
Game mechanics and UI implementation for fighter agent | bar: April WK 06 to April WK 09
Testing and Troubleshooting | bar: April WK 09 to May WK 13
AI Agents Development Using Unity ML Agent Toolkit
PPO agent implementation and training | bar: May WK 14 to June WK 17
DQN agent implementation and training | bar: June WK 17 to July WK 21
Testing and Troubleshooting | bar: June WK 15 to July WK 22
Comparative analysis | bar: July WK 22 to 2024-08-29 WK 25
Finalisation
Finalising the project, viva slides preparation & submission | bar: 2024-08-29 WK 25 to 2024-08-29 WK 27